## Plan
Phase | ID | Task | Hours | Deliverables | Start | End | Duration (days)
Requirements & Analysis | R1 | Stakeholder sync & scope lock | 4 | Final report (scope), Code-BLEU plan | 2025-09-01 | 2025-09-01 12:00 | 0.5
Requirements & Analysis | R2 | Datasets & benchmark selection (e.g., HumanEval/MBPP/CodeXGLUE) | 8 | Benchmarking scripts, Code-BLEU reports | 2025-09-01 12:00 | 2025-09-02 12:00 | 1
Requirements & Analysis | R3 | Define metrics (Code-BLEU/BLEU) & success thresholds (SLOs) | 6 | Code-BLEU reports, Final report | 2025-09-02 12:00 | 2025-09-03 06:00 | 0.75
Requirements & Analysis | R4 | Experiment backlog & risk register | 4 | Final report | 2025-09-03 06:00 | 2025-09-03 18:00 | 0.5
System Design | D1 | Inference environment architecture (full vs. compressed) | 8 | Benchmarking scripts, Routing POC | 2025-09-08 | 2025-09-09 | 1
System Design | D2 | Compression plan (quantization, distillation, pruning) | 8 | Benchmarking scripts | 2025-09-09 | 2025-09-10 | 1
System Design | D3 | Routing design (complexity signals, thresholds, fallback) | 6 | Routing POC | 2025-09-10 | 2025-09-10 18:00 | 0.75
System Design | D4 | Dashboard schema + wireframes; experiment tracking | 4 | Interactive dashboard | 2025-09-10 18:00 | 2025-09-11 06:00 | 0.5
Implementation | I1 | Benchmarking runner (timers, memory, logging, configs) | 16 | Benchmarking scripts | 2025-09-15 | 2025-09-17 | 2
Implementation | I2 | Compression pipelines (quantization + one distillation) | 20 | Benchmarking scripts | 2025-09-17 | 2025-09-19 12:00 | 2.5
Implementation | I3 | Evaluation harness (BLEU/Code-BLEU integration) | 12 | Code-BLEU reports | 2025-09-19 12:00 | 2025-09-21 | 1.5
Implementation | I4 | Routing POC app (model selection service + API) | 20 | Routing POC | 2025-09-21 | 2025-09-23 12:00 | 2.5
Implementation | I5 | Dashboard MVP (ETL, plots, Pareto views) | 16 | Interactive dashboard | 2025-09-23 12:00 | 2025-09-25 12:00 | 2
Verification & Analysis | V1 | Full experiment sweep & ablations | 24 | Benchmarking scripts, Code-BLEU reports | 2025-10-06 | 2025-10-09 | 3
Verification & Analysis | V2 | Code-BLEU reports & qualitative error analysis | 12 | Code-BLEU reports, Final report | 2025-10-09 | 2025-10-10 12:00 | 1.5
Verification & Analysis | V3 | Router tuning (thresholds/Pareto frontier) | 12 | Routing POC | 2025-10-10 12:00 | 2025-10-12 | 1.5
Verification & Analysis | V4 | Dashboard polish + usability checks | 8 | Interactive dashboard | 2025-10-12 | 2025-10-13 | 1
Deployment & Documentation | P1 | Cloud deployment recommendations & cost model | 10 | Final report (deployment recommendations) | 2025-10-20 | 2025-10-21 06:00 | 1.25
Deployment & Documentation | P2 | Packaging & reproducibility (scripts, configs) | 8 | Benchmarking scripts, Routing POC | 2025-10-21 06:00 | 2025-10-22 06:00 | 1
Deployment & Documentation | P3 | Final report & presentation deck | 14 | Final project report | 2025-10-22 06:00 | 2025-10-24 | 1.75

## Phase Summary
Phase | Hours
Implementation | 84
Verification & Analysis | 56
Deployment & Documentation | 32
System Design | 26
Requirements & Analysis | 22